## Release Planning
Project Name | Car Purchasing |  |  | Release #5 Planning
Team Members | Ebrahem (PM) |  |  | Start Date |  |  | End Date
| Arsany |  |  | 2025-10-05 |  |  | 17/5/2025
| Ehab |  |  | Deliverables
| Anas |  |  | Test Strategy - Test Execution - Bug Report
Abdelaziz
| Omar |  |  | Customer: Amr |  |  | Coach: Omar
Work package ID |  | Work package Name | Task ID |  | Task Name | Owner |  | Time | Reviewer | Time
WP_1 |  | Testing | SCRUM-104 |  | Test Admin | Arsany |  | 2 | Ebrahem | 1
|  |  | SCRUM-105 |  | Test Login | Abdelaziz |  | 4 | Anas | 1
|  |  | SCRUM-106 |  | Test Register | Anas |  | 4 | Ehab | 1
|  |  | SCRUM-107 |  | Test Advertisement | Ehab |  | 2 | Arsany | 1
|  |  | SCRUM-108 |  | Test Search | Ebrahem |  | 2 | Abdelaziz | 1
|  |  | SCRUM-109 |  | Test Reserve | Omar |  | 2 | Abdelaziz | 1
WP_2 |  | Documentation | SCRUM-110 |  | Testing Strategy | Ebrahem |  | 2 | Anas | 1
|  |  | SCRUM-111 |  | Test Execution | Arsany |  | 2 | Ebrahem | 1
|  |  | SCRUM-112 |  | Bug Report | Omar |  | 2 | Arsany | 1
WP_3 |  | PM Tasks | SCRUM-113 |  | Release Planning | Ebrahem |  | 2 | ـ
|  |  | SCRUM-114 |  | Create Release Backlog | Ebrahem |  | 2 | ـ
|  |  | SCRUM-115 |  | Assign Tasks on Tracking Tool | Ebrahem |  | 2 | ـ
WP_4 |  | Comments | SCRUM-116 |  | Update RTM | Arsany |  | 2 | Omar | 1
|  |  | SCRUM-117 |  | Update CIL | Ehab |  | 1 | Ebrahem | 1
|  |  | SCRUM-118 |  | Edit Email format in Register | Omar |  | 1 | Arsany | 1

## Estimated Time
Name | Available Time | Planed Time | Actual Time
Ebrahem | 13 | 12
Arsany | 8 | 9
Ehab | 5 | 4
Anas | 6 | 6
Abdelaziz | 6 | 6
Omar | 7 | 6
Total | 45 | 43 | 0