## Release Planning
Project Name | Car Purchasing |  |  | Release #3 Planning
Team Members | Ebrahem (PM) |  |  | Start Date |  |  | End Date
| Arsany |  |  | 26/4/2025 |  |  | 2025-03-05
| Ehab |  |  | Deliverables
Anas
Abdelaziz
| Omar |  |  | Customer: Amr |  |  | Coach: Omar
Work package ID |  | Work package Name | Task ID |  | Task Name | Owner |  | Time | Reviewer | Time
WP_1 |  | Design | SCRUM-59 |  | Class Diagram | Omar |  | 4H | Ehab | 3H
|  |  | SCRUM-60 |  | ERD | Anas |  | 4H | Ehab | 2H
|  |  | SCRUM-61 |  | End-to-End Scenario | Abdelaziz |  | 4H | Anas | 2H
|  |  | SCRUM-62 |  | High level system design | Omar |  | 3H | Anas | 2H
|  |  | SCRUM-64 |  | UI | Omar |  | 3H | Abdelaziz | 1H
|  |  | SCRUM-70 |  | Login Validation flow chart | Arsany |  | 2H | Abdelaziz | 2H
|  |  | SCRUM-71 |  | Registration Validation flow chart | Abdelaziz |  | 3H | Ebrahem | 1H
|  |  | SCRUM-72 |  | Search Validation flow chart | Ebrahem |  | 2H | Abdelaziz | 1H
|  |  | SCRUM-73 |  | Advertisement Validation flow chart | Ehab |  | 3H | Ebrahem | 1H
|  |  | SCRUM-77 |  | Admin Validation flow chart | Anas |  | 3H | Ehab | 1H
WP_2 |  | Comments | SCRUM-63 |  | RTM | Arsany |  | 2H | Ebrahem | 1H
|  |  | SCRUM-65 |  | Metrics for indicators | Arsany |  | 2H | Ebrahem | 1H
|  |  | SCRUM-66 |  | Edit SRS | Arsany |  | 2H | Ebrahem | 1H
|  |  | SCRUM-67 |  | Edit CRS | Arsany |  | 2H | Ebrahem | 1H
|  |  | SCRUM-68 |  | Edit SIQ | Arsany |  | 2H | Ebrahem | 1H
|  |  | SCRUM-79 |  |  | Arsany |  |  | Ebrahem | 1H
|  |  | SCRUM-70 |  | Edit Test cases | Arsany |  | 2H | Ebrahem | 1H
WP_3 |  | PM Tasks | SCRUM-74 |  | Release Planning | Ebrahem |  | 3H | ـ
|  |  | SCRUM-75 |  | Create Release Backlog | Ebrahem |  | 1H | ـ
|  |  | SCRUM-76 |  | Assign Tasks on Tracking Tool | Ebrahem |  | 1H | ـ
WP_4 |  | Development | SCRUM-78 |  | Development of Login page | Omar |  | 5H | Ehab | 3H
|  |  | SCRUM-79 |  | Development of Registration page | Omar |  | 3H | Abdelaziz | 3H

## Estimated Time
Name | Available Time | Planed Time | Actual Time
Ebrahem | 16 | 15
Arsany | 15 | 14
Ehab | 15 | 12
Anas | 10 | 9
Abdelaziz | 14 | 14
Omar | 19 | 18
Total | 89 | 82 | 0