## Release Planning
Project Name | Car Purchasing |  |  | Release #2 Planning
Team Members | Ebrahem (PM) |  |  | Start Date |  |  | End Date
| Arsany |  |  | 2025-12-04 |  |  | 26/4/2025
| Ehab |  |  | Deliverables
| Anas |  |  | SRS - Test Cases - PM Taskes - Release #1 comments fixing
Abdelaziz
| Omar |  |  | Customer: Amr |  |  | Coach: Omar
Work package ID |  | Work package Name | Task ID |  | Task Name | Owner |  | Time | Reviewer | Time
WP_1 |  | SRS | SRS_FR_01 |  | SRS Login | Abdelaziz |  | 4H | Omar | 1H
|  |  | SRS_FR_02 |  | SRS Registration | Arsany |  | 4H | Ehab | 2H
|  |  | SRS_FR_03 |  | SRS Advertisment | Ehab & Omar |  | 3H | Anas | 2H
|  |  | SRS_FR_04 |  | SRS Admin | Anas |  | 3H | Arsany | 2H
|  |  | SRS_FR_05 |  | SRS WebApp | Omar |  | 3H | Ebrahem | 1H
|  |  | SRS_FR_06 |  | SRS Search | Ebrahem |  | 3H | Abdelaziz | 2H
|  |  | SRS_FR_07 |  | SRS Reserve | Anas |  | 3H | Ehab | 1H
WP_2 |  | Test Cases | Test_FR_01 |  | Test Login | Arsany |  | 2H | Anas | 2H
|  |  | Test_FR_02 |  | Test Registration | Abdelaziz & Omar |  | 6H | Ehab | 2H
|  |  | Test_FR_03 |  | Test Advertisment | Anas |  | 6H | Omar | 2H
|  |  | Test_FR_04 |  | Test Admin | Ebrahem |  | 4H | Arsany | 2H
|  |  | Test_FR_05 |  | Test WebApp | Ehab |  | 30MIN | Abdelaziz | 1H
|  |  | Test_FR_06 |  | Test Search | Ehab |  | 3H | Omar | 2H
|  |  | Test_FR_07 |  | Test Reserve | Arsany |  | 3H | Ehab | 1H
WP_3 |  | Comments of Release #1 | PMP_SEC_1&2 |  | Fix Section 1&2 | Omar |  | 2H | Ehab | 1H
|  |  | PMP_SEC_4 |  | Fix Section 4 | Ehab |  | 2H | Omar | 1H
|  |  | PMP_SEC_5&6 |  | Fix Section 5&6 | Arsany |  | 2H | Anas | 1H
|  |  | PMP_SEC_7&8 |  | Fix Section 7&8 | Anas |  | 4H | Arsany | 1H
|  |  | PMP_SEC_9 |  | Fix Section 9 | Abdelaziz |  | 4H | Ebrahem | 1H
|  |  | PMP_SEC_11 |  | Fix Section 11 | Ebrahem |  | 2H | Abdelaziz | 2H
WP_4 |  | PM Tasks | PM_Task_1 |  | Release Planning | Ebrahem |  | 5H | ـ
|  |  | PM_Task_2 |  | Create Release Backlog | Ebrahem |  | 3H | ـ
|  |  | PM_Task_3 |  | Assign Tasks on Tracking Tool | Ebrahem |  | 2H | ـ

## Estimated Time
Name | Available Time | Planed Time | Actual Time
Ebrahem | 22 | 21
Arsany | 18 | 16
Ehab | 15 | 14
Anas | 18 | 18
Abdelaziz | 20 | 16
Omar | 16 | 15.5
Total | 109 | 100.5