## Release Planning
Project Name | Car Purchasing |  |  | Release #4 Planning
Team Members | Ebrahem (PM) |  |  | Start Date |  |  | End Date
| Arsany |  |  | 2025-03-05 |  |  | 2025-10-05
| Ehab |  |  | Deliverables
Anas
Abdelaziz
| Omar |  |  | Customer: Amr |  |  | Coach: Omar
Work package ID |  | Work package Name | Task ID |  | Task Name | Owner |  | Time | Reviewer | Time
WP_1 |  | User Interface Layer | SCRUM-83 |  | Home Page | Arsany |  | 2 | Ebrahem | 1
|  |  | SCRUM-84 |  | Login Page | Abdelaziz |  | 4 | Anas | 1
|  |  | SCRUM-85 |  | Register Page | Anas |  | 2 | Ehab | 1
|  |  | SCRUM-86 |  | Advertisment Page | Ehab |  | 2 | Arsany | 1
|  |  | SCRUM-87 |  | Create User Page | Ebrahem |  | 2 | Abdelaziz | 1
|  |  | SCRUM-88 |  | User management Page | Omar |  | 2 | Abdelaziz | 1
|  |  | SCRUM-89 |  | Delete User Page | Omar |  | 2 | Ehab | 1
|  |  | SCRUM-90 |  | User Details | Arsany |  | 2 | Omar | 1
WP_2 |  | App Layer | SCRUM-91 |  | User Controller | Omar |  | 2 | Anas | 1
|  |  | SCRUM-92 |  | Addvertisment Controller | Arsany |  | 2 | Ebrahem | 1
|  |  | SCRUM-93 |  | Login | Ebrahem |  | 2 | Arsany | 1
|  |  | SCRUM-94 |  | Register | Ehab |  | 2 | Omar | 1
|  |  | SCRUM-95 |  | App DB Context | Anas |  | 2 | Ehab | 1
SCRUM-96
WP_3 |  | Database Layer | SCRUM-97 |  | Create User Table | Arsany |  | 2 | Ehab | 1
|  |  | SCRUM-98 |  | Create Addvertisment Table | Ehab |  | 2 | Omar | 1
WP_3 |  | PM Tasks | SCRUM-80 |  | Release Planning | Ebrahem |  | 2 | ـ
|  |  | SCRUM-81 |  | Create Release Backlog | Ebrahem |  | 2 | ـ
|  |  | SCRUM-82 |  | Assign Tasks on Tracking Tool | Ebrahem |  | 2 | ـ
WP_4 |  | Comments | SCRUM-98 |  | Create CLI | Omar |  | 2 | Anas | 1
|  |  | SCRUM-99 |  | Edit flow charts | Arsany |  | 2 | Ebrahem | 1
|  |  | SCRUM-100 |  | Edit sequence Diagram | Ebrahem |  | 2 | Arsany | 1
|  |  | SCRUM-101 |  | Edit class diagram | Ehab |  | 2 | Omar | 1
|  |  | SCRUM-102 |  | Update GUI | Anas |  | 2 | Ehab | 1

## Estimated Time
Name | Available Time | Planed Time | Actual Time
Ebrahem | 17 | 15 | 15
Arsany | 14 | 13 | 13
Ehab | 16 | 14 | 15
Anas | 10 | 9 | 9
Abdelaziz | 9 | 6 | 7
Omar | 13 | 11 | 11
Total | 79 | 68 | 70