## Sheet1
Change ID | Change Description | Requested By | Date of Request | Area Affected | Impact Description | Severity (High/Medium/Low) | Affected Stakeholders | Approval Status | Time Requested
CHG-001 | Add upload image field in create Advertisement | Eng/ Hassan | 17/5/2025 | Backend, UI CRS, SRS Test cases, design | Affect data base architecture Source code create() method CRS add new CRS in Advertisement feature SRS add new SRS in Advertisement feature Test cases add new test cases for Advertisement feature | Low | Developers | Pending | 1 H
CHG-002 | Make the Admin can not delete him self | Eng/ Hassan | 17/5/2025 | Backend CRS, SRS Test cases, design | Source code delete_user() method CRS add new CRS in Admin feature SRS add new SRS in Admin feature test cases add new test cases for Admin feature | High | Admin | Pending | 1 H